## Slide 1
Baseline Comparison
Data Date: 24 Sep 2026
2026
2027
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Civil & Enabling
Structure
MEP & Fit-out
Site Establishment
Bulk Earthworks
Drainage & Services
Enabling Works Complete
Foundations — Zone A
Foundations — Zone B
Pile Caps & Ground Beams
Structure Complete
Services Design
Mechanical Rough-in
Fit-out & Finishes
Practical Completion
5 Jan 2026 – 6 Mar 2026
+7d
9 Feb 2026 – 1 May 2026
+14d
9 Mar 2026 – 17 Jul 2026
+17d
17 Jul 2026
+17d
11 May 2026 – 11 Sep 2026
+14d
13 Jul 2026 – 13 Nov 2026
−14d
1 Sep 2026 – 29 Jan 2027
29 Jan 2027
3 Aug 2026 – 15 Jan 2027
+14d
16 Nov 2026 – 30 Apr 2027
+14d
1 Feb 2027 – 25 Jun 2027
+21d
25 Jun 2027
+21d
Progress Schedule
Baseline Schedule
GanttSnap

## Slide 2
Executive Overview
Data Date: 24 Sep 2026
2026
2027
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Civil & Enabling
Structure
MEP & Fit-out
Site Survey
5 Jan 2026 – 27 Feb 2026
Site Clearance
2 Feb 2026 – 17 Apr 2026
Utilities Diversion
2 Mar 2026 – 30 Jun 2026
Enabling Works Complete
30 Jun 2026
Piling — Zone A
4 May 2026 – 28 Aug 2026
Piling — Zone B
6 Jul 2026 – 27 Nov 2026
Pile Caps & Ground Beams
1 Sep 2026 – 29 Jan 2027
Structure Complete
29 Jan 2027
MEP Design
3 Aug 2026 – 29 Jan 2027
Mechanical Rough-in
1 Dec 2026 – 28 May 2027
Fit-out & Finishes
1 Mar 2027 – 30 Jul 2027
Practical Completion
30 Jul 2027
Completed / In Progress
GanttSnap

## Slide 3
Portfolio Roadmap
Data Date: 24 Sep 2026
2026
2027
Q1 2026
Q2 2026
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Technology
Digital
Operations
Network Upgrade
Cloud Migration
Cybersecurity
Customer Portal
Mobile Platform
Data & Analytics
ERP Programme
Process Excellence
Supply Chain
Infrastructure Assessment
Core Network Rollout 31%
Cloud Readiness 97%
Workload Migration
Security Baseline
Zero Trust Implementation 16%
UX Research & Design
Portal Development 54%
Mobile App v2 Build 97%
Mobile App v3
Data Platform Build 68%
BI Dashboard Rollout
ERP Design & Config 98%
Pilot & Full Rollout
Process Mapping
Automation Rollout 8%
Supplier Onboarding 97%
Logistics Optimisation
Completed / In Progress
GanttSnap